## Final
Local project reference | REC Number | IRAS Number | Project Full title | IRAS Categories | Study Design | HRA approval date | Governance Route | Commercial or Non Commercial | Project site date site invited | Project site date site selected | Project site status | Date Study Initiated | Project site date site confirmed by sponsor | Project site date site confirmed | Project site Date Start | Project site date initiation visit | Project site date open to recruitment | First site participant consented (any) | First site participant recruited (org) | Performance in Initiation (PI) required? | PI: Has the 70 day benchmark been met? | PI: Reason benchmark missed | PI: Responsibility | PI: Report comments (HRA Approval delay) | PI: Report comments (Site Confirmation delay) | PI: Report comments (recruitment delay) | GOSH PID notes | Principal Investigator | Project site date non confirmation | Project site non confirmation status | Reason for missing HLO9B (Non-Commercial 62 days) | Reason for missing HLO9A (Commercial - 80 days) | Harmonised Site (HLO9)? | Reason for delay | Responsibility | Comments
18BA25 | 21/LO/0563 | 260492 | Homonymous Hemianopia in Childhood (HHIC) | Other clinical trial to study a novel intervention or randomised clinical trial to compare interventions in clinical practice |  |  |  |  | 2021-10-12 | 2022-10-12 | Open |  | 2022-10-13 | 2022-10-13 |  |  | 2022-10-13 | 2023-05-04 | 2023-05-04 | YES - clinical trial | [7 empty] | Sian Handley
18GE12 | 22/WA/0005 | 281209 | The Growth Hormone Deficiency Reversal Trial: Effect on final height of discontinuation vs continuation of growth hormone treatment in pubertal children with isolated growth hormone deficiency – A non-inferiority randomised controlled trial | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2018-07-13 | 2022-11-28 | Project site in setup |  |  | 2023-06-13 | [5 empty] | YES - clinical trial | [7 empty] | Prof Mehul Dattani | [6 empty] | NHS Site | Q1 - Delays in setting up the ward to deliver the service.
19BO16 | 19/SC/0023 | 255292 | An Open-Label Roll-Over Study to Evaluate the Long-Term Safety and Efficacy of DCR PHXC Solution for Injection (subcutaneous use) in Patients with Primary Hyperoxaluria | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2019-05-13 | 2022-11-14 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Wesley Hayes | [6 empty] | Neither | Q1 - Roll-over study and patients on the original study will not need to roll over until Nov-23 at the earliest. Due to prioritisation, the setup is continuing but it is like this study will not open until nearer the time required
19NM08 | 20/LO/1145 | 286790 | A Phase 1/2 Randomised, Placebo-Controlled, Double-Blinded, Single Crossover Study to Determine the Safety and Efficacy of Tamoxifen Therapy for Myotubular Myopathy (XLMTM) | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2019-03-07 | 2022-08-01 | Open |  | 2022-08-25 | 2022-08-25 |  | 2022-08-18 | 2022-09-09 | 2022-09-28 | 2022-09-28 | YES - clinical trial | [7 empty] | Dr Giovanni Baranello
19NM13 | 20/LO/1222 | 287014 | Microdystrophin (GNT0004) Gene Therapy Clinical Trial in Duchenne Muscular Dystrophy A phase I/II/III study with a dose determination part followed by an efficacy and safety evaluation, quadruple blind placebo-controlled part and then by a long term safety follow up part, in ambulant boys | Clinical trial of an investigational medicinal product |  | 2021-05-05 |  |  | 2019-04-17 | 2022-12-23 | Project site in setup |  | 2023-07-10 | 2023-07-10 |  | 2023-07-10 |  |  |  | YES - clinical trial | [7 empty] | Prof Francesco Muntoni | [6 empty] | Sponsor | Q1 - Delay with budget negotiation. Sponsor delay by setting up budget incorrectly on CPMS.
20BI10 | 22/LO/0643 | 294472 | Children’s Adaptive Deep brain stimulation for Epilepsy Trial - Pilot |  | Clinical investigation or other study of a medical device | 2022-12-06 |  | Non Commercial | 2020-03-02 | 2023-01-11 | Open |  |  | 2023-05-02 |  |  | 2023-06-02 |  |  | YES - clinical trial | [7 empty] | Martin Tisdall | [6 empty] | NHS Site | Q1 - Delays with internal finance review as original Soecat was incorrect
20BI34 | 21/NE/0229 | 1003734 | A Phase III study of JR-141 in Mucopolysaccharidosis type II (Hunter Syndrome) Patients | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2020-11-13 | 2022-08-01 | Open |  |  | 2022-08-30 |  | 2022-08-30 | 2022-12-14 |  |  | YES - clinical trial | [5 empty] | Pharmacy Greenlight granted 18/04/2023, prior to this it was not possible to recruit patients at GOSH |  | Dr James Davison | [6 empty] | Neither | Q1 - Delayed due to the sponsor awaiting delivery of IMP
20CB37 | 21/SC/0110 | 1003535 | A PHASE I/II, OPEN-LABEL, MULTICENTER STUDY EVALUATING THE SAFETY, PHARMACOKINETICS, AND EFFICACY OF ALECTINIB IN PEDIATRIC PATIENTS WITH ALK FUSION POSITIVE SOLID OR CNS TUMORS FOR WHOM PRIOR TREATMENT HAS PROVEN TO BE INEFFECTIVE OR FOR WHOM THERE IS NO CURATIVE STANDARD TREATMENT AVAILABLE | Clinical trial of an investigational medicinal product |  | 2021-06-17 |  | Commercial | 2021-05-06 | 2022-08-01 | Open |  | 2022-10-20 | 2022-09-29 |  |  | 2022-10-20 | 2023-05-04 | 2023-05-12 | YES - clinical trial | [7 empty] | Dr Darren Hargrave | [6 empty] | Neither | Q1 - Rare disease drug therapy. First screening this month.
21BI21 | 22/EM/0077 | 1004978 | A Phase 3 Study of PTC923 in Subjects with Phenylketonuria | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-06-06 |  | Commercial | 2022-02-15 | 2022-09-05 | Closed to recruitment - in follow up |  | 2022-11-22 | 2022-11-22 |  |  | 2022-11-22 | 2022-11-30 | 2022-11-30 | YES - clinical trial | [6 empty] | Budget agreed 26.09.22. Contract signed 18.11.22 | Dr Anupam Chakrapani
21BI22 | 22/LO/0485 | 1005744 | A Phase 3 Open-Label Extension Study of PTC923 in Phenylketonuria | Clinical trial of an investigational medicinal product |  |  |  |  | 2022-06-23 | 2022-11-14 | Open |  | 2023-02-20 | 2023-02-17 |  | 2023-02-08 | 2023-02-20 | 2023-02-22 | 2023-02-22 | YES - clinical trial | [7 empty] | Dr Anupam Chakrapani | [6 empty] | Neither | Q1 - Delays in contract agreement
21BI26 | 22/LO/0079 | 305839 | A Randomized, Double-Blind, Placebo-Controlled Study to Evaluate the Safety and Efficacy of Crinecerfont (NBI-74788) in Pediatric Subjects with Classic Congenital Adrenal Hyperplasia, Followed by Open-Label Treatment |  | Clinical trial of an investigational medicinal product | 2022-04-21 |  | Commercial | 2021-04-12 | 2022-08-01 | Closed to recruitment - in follow up |  |  | 2022-10-21 |  | 2022-08-23 | 2022-10-26 | 2022-11-16 | 2022-11-16 | YES - clinical trial | [6 empty] | Discussions regarding homecare & amendment for patients to be admitted overnight for taking early morning bloods the next day, as some patients may need to stop their regular night dose of medicine before early morning bloods. The PI felt this is important in terms of patient safety. Delays with radiology capacity review. | Prof Mehul Dattani |  |  |  |  | No |  | Neither | Q1 - Delays in costing and contract. Delays in radiology capacity review.
21BI30 | 22/LO/0341 | 1005057 | Interventional, randomized, double-blind, parallel-group, placebo-controlled study to evaluate the efficacy and safety of IV eptinezumab in adolescents (12-17 years) for the preventive treatment of chronic migraine | Clinical trial of an investigational medicinal product |  |  |  |  | 2021-08-03 | 2022-12-12 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Prab Prabhakar |  |  |  |  | No |  | Neither | Q1 - Budget negotiations caused delay, however there has been a recent change to the pharmacy manual which means unblinded nurses are required which had not previously been accounted for in the pharmacy / clinical delivery team set up processes or budget.
21BI44 | 22/EE/0014 | 1004459 | AN OPEN-LABEL MULTICENTER STUDY TO EVALUATE THE PHARMACOKINETICS, PHARMACODYNAMICS, AND SAFETY OF INEBILIZUMAB IN PEDIATRIC SUBJECTS WITH NEUROMYELITIS OPTICA SPECTRUM DISORDER | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2021-05-21 | 2022-09-26 | Open |  | 2022-10-14 | 2022-09-30 |  | 2022-10-03 | 2022-10-14 |  |  | YES - clinical trial | [7 empty] | Dr Cheryl Hemingway | [6 empty] | Neither | Q1 - No eligible patients.
21BI49 | 22/SW/0065 | 313309 | Implementation of an artificial intelligence module on the online imaging portal MYO-Share for guiding the diagnosis of muscle disease | Clinical investigation or other study of a medical device |  |  |  |  | 2021-12-02 | 2022-07-06 | Project site in setup |  | 2022-10-12 | 2022-10-12 | [5 empty] | YES - clinical trial | [7 empty] | Anna Sarkozy | [6 empty] | NHS Site | Q1 - Delays in IT and CyberSec approvals, confirmed but awaiting software installation to carry out anonymisation of MRIs.
21BO01 | 22/NE/0027 | 301140 | A Double-Blind, Placebo-Controlled, Dose Escalation Study to Assess the Efficacy, Safety and Pharmacokinetics of Voclosporin in Adolescents with Lupus Nephritis | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2021-12-17 | 2022-11-01 | Project site in setup |  |  | 2023-03-15 | [5 empty] | YES - clinical trial | [7 empty] | Prof Stephen Marks |  |  |  |  | Yes |  | Neither | Q1 - Sponsor has informed GOSH that recruitment for this study will be delayed for approx. 10 months from 07/07/2022 due to the manufacturing of the IMP
21BO05 | 21/LO/0511 | 300087 | A Phase 3b Multicenter Open-label Trial of the Safety, Tolerability, and Efficacy of Tolvaptan in Infants and Children 28 days to less than 18 years of Age with Autosomal Recessive Polycystic Kidney Disease (ARPKD) | Clinical trial of an investigational medicinal product |  |  |  |  | 2021-03-22 | 2022-11-17 | Project site in setup |  | 2023-07-03 | [6 empty] | YES - clinical trial | [7 empty] | Dr Matko Marlais |  |  |  |  | No |  | Neither | Q1 - Delays due to budget negotiations
21BO08 |  | 300574 (previously 298296) | A Phase 3b Multicenter Open-label Trial of the Safety, Tolerability, and Efficacy of Tolvaptan in Infants and Children 28 days to less than 12 weeks of Age with Autosomal Recessive Polycystic Kidney Disease (ARPKD) | [5 empty] | 2021-07-01 | 2023-05-15 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Dr Matko Marlais |  |  |  |  | Yes |  | Neither | Q1 - Delays in contracts and budget
21BO10 | 21/NW/0338 | 301477 | A Phase 3, Randomized, Placebo-Controlled, Double-Blinded, Multicenter Study to Evaluate the Efficacy and Safety of Pegcetacoplan in Patients with C3 Glomerulopathy or Immune-Complex Membranoproliferative Glomerulonephritis | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2021-11-09 | 2023-02-13 | Open |  |  | 2023-03-07 |  | 2023-04-26 | 2023-05-12 |  |  | YES - clinical trial | [6 empty] | DT - SIV took place on 26th April, however, it was identified that the lab kits are expiring soon so new stock is required. Also, the pumps which will be provided by the sponsor to administer the medication are yet to be delivered and are to go through biomedical clearance before we can use. | Prof Stephen Marks | [6 empty] | Neither | Q1 - Not enough eligible patients
21BO15 | 21/WA/0248 | 1003891 | A PHASE II, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER STUDY TO EVALUATE THE EFFICACY, SAFETY, AND PHARMACOKINETICS OF OBINUTUZUMAB WHEN GIVEN IN COMBINATION WITH MYCOPHENOLATE MOFETIL AND CORTICOSTEROIDS IN ADOLESCENT PARTICIPANTS WITH ACTIVE CLASS III OR IV LUPUS NEPHRITIS | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2021-09-28 |  | Commercial | 2021-05-20 | 2022-08-01 | Open |  | 2022-10-13 | 2022-10-04 |  | 2022-10-12 | 2022-10-13 |  |  | YES - clinical trial | [6 empty] | Radiology not able to review as GA/US requirements not included in study docs. Amendment required. Contract signed Oct 22. Study opened in Oct 22 but EPIC pharmacy build delayed which delayed recruitment. | Dr Matko Marlais | [6 empty] | Neither | Q1 - Not enough eligible patients
21BO28 | 21/NE/0219 | 1004175 | 6 month multicenter, randomized, double-blind, placebo-controlled study to evaluate the efficacy, safety and PK/PD of an age-and body weight-adjusted oral finerenone regimen, in addition to an ACE-I or ARB, for the treatment of children, 6 months to < 18 years of age, with chronic kidney disease and proteinuria | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2021-11-12 | 2022-09-05 | Open |  | 2022-10-12 | 2022-10-11 |  | 2022-09-02 | 2022-10-12 | 2022-12-22 | 2022-12-22 | YES - clinical trial | [7 empty] | Prof Rukshana Shroff
21CB18 | 21/LO/0752 | 1004004 | CiproPAL (Ciprofloxacin Prophylaxis in Acute Leukaemia): A randomised trial to assess the use of ciprofloxacin prophylaxis to prevent bacterial infection in children treated on the induction phase of the ALLTogether1 treatment protocol | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2021-09-28 | 2022-10-07 | Open |  | 2023-04-03 | 2022-11-07 |  | 2022-11-24 | 2023-04-03 | 2023-06-06 | 2023-06-06 | YES - clinical trial | [7 empty] | Dr Danny Cheng | [6 empty] | NHS Site | Q1 - Delay in setting up cost centres to order safe boxes to send patient samples.
21DC35 | 22/EE/0092 | 302854 | A Phase 1/2, Single-arm Study to Evaluate the Safety, Pharmacokinetics, and Antitumor Activity of Avapritinib in Pediatric Patients with Solid Tumors Dependent on KIT or PDGFRA Signaling | Clinical trial of an investigational medicinal product |  | 2022-08-12 |  |  | 2021-09-04 | 2023-01-06 | Open |  |  | 2023-02-06 |  |  | 2023-02-15 |  |  | YES - clinical trial | [7 empty] | Dr Darren Hargrave | [6 empty] | Sponsor | Q1 - When GOSH opened, slots were on hold pending further PK analysis. It is possible Sponsor may need to reopen some additional phase 1 slots prior to commencing the phase 2. As soon as slots reopen the team will be able to meet the recruitment target.
21GI28 | 22/LO/0383 | 1004529 | A Phase 1/2 Intracerebroventricular and Intravitreal Administration of NGN-101 for Treatment of Neuronal Ceroid Lipofuscinosis Subtype 5 (CLN5) Disease |  |  | 2022-08-04 |  |  | 2021-12-09 | 2023-02-07 | Open |  | 2023-03-31 | 2023-02-28 |  |  | 2023-03-31 | 2023-04-11 | 2023-05-17 | YES - clinical trial | [7 empty] | Dr Paul Gissen
21HL04 | 23/LO/0010 | 322370 | A randomised controlled trial of no routine gastric residual monitoring to guide enteral feeding in paediatric intensive care units. | Other clinical trial to study a novel intervention or randomised clinical trial to compare interventions in clinical practice |  | 2023-05-15 | HRA Approval |  | 2023-01-23 | 2023-05-26 | Open |  | 2023-07-03 | 2023-07-03 |  |  | 2023-07-04 |  |  | YES - clinical trial | [7 empty] | Prof Katherine Brown
21NC12 | 22/NW/0019 | 300846 | A 20-Week Multicenter, Randomized, Double-Blind, Placebo-Controlled Trial of EPX-100 (Clemizole Hydrochloride) as Adjunctive Therapy in Patients with Dravet Syndrome (ARGUS Trial) | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-04-13 |  | Commercial | 2022-02-14 | 2023-03-14 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Helen Cross |  |  |  |  | No |  | Neither | Q1 - Substantial amendment submitted during setup which requires re-review of delivery planning and budget
21NM25 | 21/EM/0256 | 1004228 | A TWO-PART, SEAMLESS, MULTI-CENTER, RANDOMIZED, PLACEBO-CONTROLLED, DOUBLE-BLIND STUDY TO INVESTIGATE THE SAFETY, TOLERABILITY, PHARMACOKINETICS, PHARMACODYNAMICS AND EFFICACY OF RO7204239 IN COMBINATION WITH RISDIPLAM (RO7034067) IN AMBULANT PATIENTS WITH SPINAL MUSCULAR ATROPHY | Clinical trial of an investigational medicinal product |  |  |  |  | 2021-07-27 | 2022-08-22 | Open |  | 2023-02-14 | 2023-02-10 |  | 2023-02-28 | 2023-02-14 |  |  | YES - clinical trial | [7 empty] | Dr Mariacristina Scoto | [6 empty] | Neither | Q1 - Delay in recruitment due to strict eligibility criteria (only ambulant patients when majority are non-ambulant)
21NM28 | 22/EM/0054 | 1004906 | Phase 3, Double-Blind, Placebo-Controlled Trial to Evaluate the Efficacy and Safety of Apitegromab (SRK-015) in Patients with Later-Onset Spinal Muscular Atrophy Receiving Background Nusinersen or Risdiplam Therapy | Clinical trial of an investigational medicinal product |  | 2022-04-07 |  |  | 2021-09-10 | 2023-03-01 | Open |  | 2023-06-05 | 2023-05-26 |  | 2023-04-19 | 2023-06-05 | 2023-06-14 | 2023-06-14 | YES - clinical trial | [7 empty] | Dr Giovanni Baranello | [6 empty] | NHS Site | Q1 - Delays in pharmacy readiness
21NM32 | 21/EE/0259 | 1004329 | A Phase 3, Multi-center, Open-label Extension Study to Assess the Safety and Efficacy of Viltolarsen in Ambulant Boys with Duchenne Muscular Dystrophy (DMD) | Clinical trial of an investigational medicinal product |  |  | HRA Approval |  | 2021-10-13 | 2022-07-18 | Open |  | 2022-08-09 | 2022-08-24 |  | 2022-07-21 | 2022-08-24 | 2022-09-07 | 2022-09-07 | YES - clinical trial | [7 empty] | Dr Giovanni Baranello
22BI03 | 21/EE/0273 | 1003989 | Open-label Uncontrolled Trial to Evaluate Pharmacokinetics, Pharmacodynamics, Safety, and Activity of Efgartigimod in Children From 2 to Less Than 18 Years of Age With Generalized Myasthenia Gravis |  | Clinical trial of an investigational medicinal product | 2022-02-18 |  | Commercial | 2022-01-05 | 2022-08-22 | Suspended |  | 2023-04-11 | 2023-02-13 |  | 2023-03-03 | 2023-04-11 |  |  | YES - clinical trial | [7 empty] | Pinki Munot | [6 empty] | Neither | Q1 - Recruitment on hold by the sponsor due to submitted amendment
22BI11 | 22/SC/0156 | 1005494 | A Phase 2/3, Multicenter, Double-Blind, Randomized Study to Determine the Efficacy and Safety of DNL310 vs Idursulfase in Pediatric Participants With Neuronopathic or Non-Neuronopathic Mucopolysaccharidosis Type II | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-06-22 |  | Commercial | 2022-05-05 | 2022-08-22 | Open |  | 2022-11-24 | 2022-10-25 |  | 2022-10-26 | 2023-03-03 |  |  | YES - clinical trial | [6 empty] | Delay in recruitment due to delay in pharmacy greenlight while sponsor confirmed rounding rules (pharmacy greenlight granted 28/02/23). Cohort A opened to recruitment 07.03.23, after sponsor granted greenlight for this cohort only. TOVA training by psychology required before opening cohort B, separate greenlight to be granted for this. | Spyros Batzios |  |  |  |  | No |  | Both | Q1 - Delays with the equipment needed as well as the ongoing strikes
22BI12 | 22/LO/0312 | 1005058 | Long-term, open-label (dose-blinded), extension study of eptinezumab in children and adolescents with chronic or episodic migraine | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-07-04 |  | Commercial | 2022-04-19 | 2022-12-12 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Prab Prabhakar |  |  |  |  | No |  | Neither | Q1 - Budget negotiations caused delay, however there has been a recent change to the pharmacy manual which means unblinded nurses are required which had not previously been accounted for in the pharmacy / clinical delivery team set up processes or budget. Follow on from 20BI30, patients will roll into this.
22BI13 |  | 1006078 | A Randomized, Double-blind, Multicenter Study to Determine the Effect of Triheptanoin Compared with Even-chain, Medium-chain Triglycerides (MCT) on Major Clinical Events (MCEs) in Pediatric Patients with Long-chain Fatty Acid Oxidation Disorders (LC-FAOD) | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2023-02-09 |  | Commercial | 2022-04-21 | 2023-04-26 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Stephanie Grunewald | [6 empty] | NHS Site | Q1 - Delays in pharmacy readiness
22BI16 | 22/LO/0518 | 1005724 | Long-Term, Open-Label Extension Study to Evaluate the Safety and Tolerability of NBI-827104 in Pediatric Subjects with Epileptic Encephalopathy with Continuous Spike-and-Wave During Sleep |  | Clinical trial of an investigational medicinal product | 2022-09-01 |  | Commercial | 2022-05-20 | 2022-09-16 | Closed to recruitment - in follow up |  | 2022-09-20 | 2022-09-18 |  | 2022-09-20 | 2022-09-20 | 2022-09-29 | 2022-09-29 | YES - clinical trial | [7 empty] | Dr Suresh Pujar
22BI26 | 22/EE/0233 | 1006388 | A Phase 3B/4 Open-Label Multicenter Study Extension Study to Further Evaluate Safety, Tolerability and Efficacy of Intracerebroventricular AX 250 Treatment in Mucopolysaccharidosis Type IIIB (MPS IIIB, Sanfilippo Syndrome Type B) Patients | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-10-17 |  | Commercial | 2022-09-09 | 2022-11-24 | Open |  | 2022-12-01 | 2022-12-01 |  |  | 2022-12-01 | 2022-12-02 | 2022-12-02 | YES - clinical trial | [7 empty] | Spyros Batzios
22BI29 | 23/SC/0070 | 1006831 | AN OPEN-LABEL STUDY TO EVALUATE THE SAFETY, EFFICACY, PHARMACOKINETICS, PHARMACODYNAMICS, AND IMMUNOGENICITY OF CIPAGLUCOSIDASE ALFA/MIGLUSTAT IN BOTH ERT-EXPERIENCED AND ERT-NAÏVE PEDIATRIC SUBJECTS WITH INFANTILE-ONSET POMPE DISEASE AGED 0 TO < 18 YEARS | Clinical trial of an investigational medicinal product |  |  |  | Commercial | 2022-11-07 | 2023-03-03 | Feasibility | [8 empty] | YES - clinical trial | [7 empty] | Spyros Batzios | [6 empty] | Both | Q1 - Delays in MHRA/regulatory approvals, delays in contracts with homecare vendor by GOSH(IG+CyberSec)
22BI31 | 23/WM/0039 | 1006542 | A Phase 3 Open-Label Study of Safety of Weekly Subcutaneous Pegzilarginase in Subjects with Arginase 1 Deficiency | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product |  |  | Commercial | 2023-02-13 | 2023-02-13 | Withdrawn by Sponsor | [8 empty] | YES - clinical trial | [7 empty] | Spyros Batzios | 2023-04-12 | Sponsor declined site confirmation |  |  |  |  | Neither | Q1 - Study withdrawn
22BO05 | 22/EE/0064 | 1005163 | A Phase 2 Open Label Pilot Study to Evaluate the Safety and Efficacy of Subcutaneously Administered ELX-02 in Patients with Alport Syndrome with Col4A5 and Col4A3/4 Nonsense Mutation | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-05-04 |  | Commercial | 2022-04-04 | 2022-09-14 | Open |  | 2022-11-28 | 2022-11-25 |  | 2022-11-28 | 2022-11-28 | 2023-01-13 | 2023-01-13 | YES - clinical trial | [7 empty] | Dr Matko Marlais |  |  |  |  | No
22BO18 | 23/WS/0018 | 1007170 | A Phase 3, Multicenter, Randomized, Platform Study of p19 Inhibition of the IL-23 Pathway to Establish Efficacy in Pediatric Crohn’s Disease | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product |  |  | Commercial | 2022-07-28 | 2023-02-22 | Feasibility | [8 empty] | YES - clinical trial | [7 empty] | Dr Kelsey Jones | [6 empty] | Neither | Q1 - Delay in regulatory approvals
22CB01 | 22/EE/0222 | 1005896 | A Phase 3 Multicenter, Open-label Study to Evaluate the Efficacy, Pharmacokinetics, Safety, and Immunogenicity of Subcutaneously Administered Ustekinumab or Guselkumab in Pediatric Participants With Active Juvenile Psoriatic Arthritis (PSUMMIT-Jr) | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-11-24 |  | Commercial | 2022-01-06 | 2023-02-01 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Dr Sandrine Lacassagne | [6 empty] | NHS Site | Q1 - Delays in pharmacy readiness
22CB07 | 22/NE/0011 | 308872 | Phase 2/3, Multicenter, Randomized, Double-Blind, Placebo-Controlled Study to Assess the Safety and Efficacy of ALVR105 (Viralym-M) Compared to Placebo for the Prevention of AdV, BKV, CMV, EBV, HHV-6, and JCV Infection and/or Disease, in High-Risk Patients After Allogeneic Hematopoietic Cell Transplant | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-05-13 | HRA Approval | Commercial | 2022-03-24 | 2022-10-17 | Open | 2022-01-28 | 2022-10-21 | 2022-10-20 |  | 2022-10-18 | 2022-10-21 | 2023-03-23 | 2023-05-10 | YES - clinical trial | [7 empty] | Dr Kanchan Rao | [6 empty] | Neither | Q1 - Not enough eligible patients, families reluctant due to number of visits required
22CB18 | 22/LO/0298 | 1005245 | A randomised non-inferiority trial with nested PK to assess DTG/3TC fixed dose formulations for the maintenance of virological suppression in children with HIV infection aged 2 to <15 years old | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-10-11 |  | Non Commercial | 2022-07-04 | 2023-03-14 | Open |  |  | 2023-03-31 |  |  | 2023-05-05 | 2023-06-02 | 2023-06-02 | YES - clinical trial | [7 empty] | Alasdair Bamford
22GI01 | 22/EM/0015 | 1004498 | Effects of N-Acetyl-L-Leucine on Niemann-Pick disease type C (NPC): A Phase III, randomized, placebo-controlled, double-blind, crossover study | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-03-07 |  | Commercial | 2022-01-07 | 2022-08-01 | Closed to recruitment - in follow up |  | 2022-10-04 | 2022-10-04 |  | 2022-09-09 | 2022-10-04 | 2022-11-21 | 2022-11-21 | YES - clinical trial | [7 empty] | Dr Paul Gissen
22GR19 | 22/WA/0290 | 1006123 | AN OPEN-LABEL, SAFETY STUDY FOR PREVIOUSLY TREATED VATIQUINONE (PTC743) SUBJECTS WITH INHERITED MITOCHONDRIAL DISEASE | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-12-05 |  | Commercial | 2022-10-28 | 2022-11-07 | Open |  |  | 2023-03-29 |  | 2023-03-28 | 2023-04-03 | 2023-04-03 | 2023-04-03 | YES - clinical trial | [7 empty] | Dr Shamima Rahman | [6 empty] | NHS Site | Q1 - Delay in device approval from IG
22HL20 |  | 1006620 | A Phase 2/3 Randomized, Placebo-Controlled, Double-blind, Clinical Study to Evaluate the Efficacy, Safety, and Pharmacokinetics of Vericiguat in Pediatric Participants with Heart Failure due to Left Ventricular Systolic Dysfunction Consistent with Dilated Cardiomyopathy (VALOR) | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-12-05 |  | Commercial | 2022-06-20 | 2023-04-26 | Feasibility |  |  |  |  | 2023-05-03 |  |  |  | YES - clinical trial | [7 empty] | Dr Craig Laurence | [6 empty] | Neither | Q1 - Delays in contracts and budget
22HL24 |  | 1006644 | A Phase 2 Open-label Study to Evaluate the Safety, Tolerability, Pharmacokinetics, and Pharmacodynamics of Sotatercept (MK-7962) in Children from 1 to Less Than 18 Years of Age With PAH on Standard of Care | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2023-06-26 |  | Commercial | 2022-08-30 | 2022-11-25 | Project site in setup | [8 empty] | YES - clinical trial | [6 empty] | MHRA delays, identification of Sub-Inv pending | Dr Shahin Moledina | [6 empty] | Neither | Q1 - MHRA delays, budgeting delays
22HL26 | 22/WM/0239 | 1006429 | A Phase 3 Study Evaluating the Pharmacokinetics, Safety, and Tolerability of VX‑121/Tezacaftor/Deutivacaftor Triple Combination Therapy in Cystic Fibrosis Subjects 1 Through 11 Years of Age | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2023-02-21 |  | Commercial | 2022-06-07 | 2022-10-13 | Open |  | 2023-03-17 | 2023-03-16 |  | 2023-03-17 | 2023-03-22 | 2023-04-18 | 2023-05-11 | YES - clinical trial | [6 empty] | Original target of a minimum of 4 (2 GOSH, 2 London Hospitals /PIC referrals) was reduced to 2-4 due to competitive recruitment with a short timeframe. | Dr Gwyneth Davies | [6 empty] | Neither | Q1 - Delays in MHRA approval due to staff shortage
22IH04 | 22/LO/0382 | 1003938 | A two-cohort, open-label, single arm, multicenter study to evaluate efficacy, safety and tolerability, pharmacokinetics (PK) and pharmacodynamics (PD), of emapalumab in children and adults with macrophage activation syndrome (MAS) in Still’s disease (including systemic juvenile idiopathic arthritis and adult onset Still’s disease) or with MAS in systemic lupus erythematous | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-06-23 |  | Commercial | 2022-04-14 | 2022-10-03 | Open |  | 2022-12-07 | 2022-12-05 |  | 2022-11-23 | 2022-12-07 |  |  | YES - clinical trial | [6 empty] | Delay in setup due to discrepancy in pharmacy manual which required amendment | Dr Paul Brogan | [6 empty] | Neither | Q1 - Delay in setup ( and recruitment) due to discrepancy in pharmacy manual which required amendment. No eligible patients currently. Patients are likely to be admitted acutely unwell and will be recruited at the time of MAS diagnosis.
22NC04 | 22/EM/0089 | 1004438 | A PHASE 3, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, FIXED-DOSE, MULTICENTER STUDY TO EXAMINE THE EFFICACY AND SAFETY OF ZX008 IN SUBJECTS WITH CDKL5 DEFICIENCY DISORDER FOLLOWED BY AN OPEN-LABEL EXTENSION |  | Clinical trial of an investigational medicinal product | 2022-06-07 |  | Commercial | 2022-03-10 | 2022-10-03 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Helen Cross | [6 empty] | Neither | Q1 - Delays in costing and contract
22NM17 | 22/NE/0211 | 1006053 | Long-term follow-up of patients with spinal muscular atrophy Treated with OAV101 IT or OAV101 IV in Clinical Trials | Other clinical trial to study a novel intervention or randomised clinical trial to compare interventions in clinical practice | Clinical trial of an investigational medicinal product | 2023-02-09 |  | Commercial | 2022-07-11 | 2023-06-07 | Project site in setup |  |  | 2023-07-05 | [5 empty] | YES - clinical trial | [7 empty] | Dr Giovanni Baranello
22SH09 | 22/NE/0065 | 311790 | To evaluate the acceptability and palatability of a hypoallergenic nutritionally complete powdered amino acid formula with HMO (Human Milk Oligosaccharides) for the dietary management of cows’ milk allergy (CMA) and multiple food protein allergies (MFPA) in children over ≥1 year. | Other clinical trial to study a novel intervention or randomised clinical trial to compare interventions in clinical practice | Other clinical trial to study a novel intervention or RCT to compare interventions | 2022-05-30 |  | Commercial | 2022-05-17 | 2022-07-20 | Open |  | 2022-08-23 | 2022-08-23 |  | 2022-08-17 | 2022-08-23 | 2022-09-07 | 2022-09-07 | YES - clinical trial | Within 70 days |  |  | n/a | n/a | n/a | First patient recruited 07/09/2022. We’ve now recruited 5 patients, which was our initial target. Nestle have requested we continue to recruit. | Dr Graeme O'Connor
22SS06 | 22/LO/0412 | 1005501 | A First-in-Human, Open-Label, Dose-Escalation Study to Evaluate the Safety and Tolerability of Gene Therapy with RGX 381 for the Ocular Manifestations Associated with Neuronal Ceroid Lipofuscinosis Type 2 (CLN2) Disease | Clinical trial of an investigational medicinal product | Clinical trial of an investigational medicinal product | 2022-08-09 |  | Commercial | 2022-05-06 | 2023-02-13 | Open |  | 2023-05-12 | 2023-04-26 |  | 2023-03-09 | 2023-05-12 | 2023-05-17 | 2023-05-17 | YES - clinical trial |  |  |  |  | Delay due to budget negotiation |  |  | Robert Henderson
22SS07 | 22/LO/0611 | 290045 | A dual-cohort feasibility study to investigate the usage of a child-friendly home-monitoring tool for vision assessment for treatment planning in optic pathway gliomas. | Clinical investigation or other study of a medical device | Clinical investigation or other study of a medical device | 2022-10-26 |  | Non Commercial | 2022-06-22 | 2022-11-01 | Project site in setup |  |  | 2023-01-16 | [5 empty] | YES - clinical trial | [7 empty] | Mr Richard Bowman | [6 empty] | Sponsor | Q1 - GOSH has confirmed internally but still awaiting confirmation from Sponsor
23BI07 | 23/SC/0074 | 1007215 | A study to test whether spesolimab helps people with skin disease called Netherton syndrome | Clinical trial of an investigational medicinal product |  |  |  | Commercial | 2023-03-01 | 2023-04-25 | Project site in setup | [8 empty] | YES - clinical trial | [7 empty] | Anna Martinez | [6 empty] | Both | Q1 - MHRA delays, budgeting delays, PI considering negotiating for homecare
23CB10 | 20/SS/0072 | 255036 | A Long-term Follow-up Study of Subjects With β thalassemia or Sickle Cell Disease Treated with Autologous CRISPR-Cas9 Modified Hematopoietic Stem Cells (CTX001) | Clinical trial of an investigational medicinal product |  |  | HRA Approval | Commercial | 2023-03-16 | 2023-03-16 | Feasibility | [8 empty] | YES - clinical trial | [7 empty] | Dr Persis Amrolia | [6 empty] | Neither | Q1 - Follow-up study to be timed according the schedule of the main study, set-up not prioritised unti participants in main study have progressed, sponsor aware
23CB12 | 23/WA/0005 | 1006502 | A Phase 3b/4 Randomized, Open-label, Assessor Blinded Study, Comparing the Safety and Efficacy of Upadacitinib to Dupilumab in Subjects with Moderate to Severe Atopic Dermatitis (Level-Up) | Clinical trial of an investigational medicinal product |  |  | HRA Approval | Commercial | 2023-02-17 | 2023-04-03 | Feasibility | 2023-01-09 | [7 empty] | YES - clinical trial | [7 empty] | Gabriela Petrof | [6 empty] | Neither | Q1 - Budgeting delays at national level, regulatory approvals pending, activation delayed due to ePRO unavailability and earlier activation around Oct-23
23CB18 |  | 1006787 | A Phase 3, Open-label, 52-week Study to Assess the Safety, Tolerability, and Efficacy of Rocatinlimab (AMG 451) in Adolescent Subjects Aged ≥ 12 to < 18 years With Moderate-to-severe Atopic Dermatitis (AD) (ROCKET-Orbit) |  | Clinical trial of an investigational medicinal product |  |  | Commercial | 2023-05-30 | 2023-05-30 | Project site in setup |  | 2023-05-30 | 2023-06-30 | [5 empty] | YES - clinical trial | [7 empty] | Gabriela Petrof
23NM02 |  |  | A Phase 3 Randomized, Placebo-controlled, Double-blind Study to Evaluate the Efficacy and Safety of BBP-418 (ribitol) in Patients with Limb Girdle Muscular Dystrophy 2I (LGMD2I) |  |  |  |  | Commercial | 2023-01-16 | 2023-06-01 | Feasibility | [8 empty] | YES - clinical trial | [7 empty] | Dr Giovanni Baranello
23HL08 |  | 1007411 | A Phase 3, Open-label Study Evaluating the Long-term Safety and Efficacy of Vanzacaftor/Tezacaftor/Deutivacaftor Triple Combination Therapy in Cystic Fibrosis Subjects 1 Year of Age and Older | Clinical trial of an investigational medicinal product |  |  |  | Commercial | 2023-03-24 | 2023-03-24 | Feasibility | [8 empty] | YES - clinical trial | [5 empty] | Dr Gwyneth Davies | [8 empty] | Neither | Q1 - Follow-up study, sponsor prioritised the main one, participants to roll over from main study in due course